## Sheet1
AGM Preparation Checklist
Input your AGM date below to calculate the proposed dates for the steps leading up to your AGM.
Check your constitution for exactly what applies to your organisation.
Activity | Date (per constitution or best practice) | Date (proposed) | Date (actual)
Finalise date and time for AGM | Aim for at least 8 weeks prior to AGM | 2024-05-05
Ensure the financial statements and audit report are prepared and available for members to review well in advance of the AGM. Note: The financial statements and audit or verification report MUST be presented at the AGM | Aim for at least 28 days prior to AGM | 2024-06-02
Officially call for nominations for management committee positions and expressions of interest for any non-committee positions. Ideally circulate position descriptions with the call for nominations. The call for nominations can be via correspondence, email, web/social media announcements or on a noticeboard | At least 28 days prior to AGM | 2024-06-02
Finalise venue and catering (if relevant) | At least 28 days prior to AGM | 2024-06-02
Officially call the AGM by giving notice to members. Include detail of the date, time and venue and all business to be transacted at the AGM. The management committee is to decide the way in which notice is to be given to members (e.g. correspondence; email; web/social media announcement; noticeboard) | At least 14 days prior to AGM | 2024-06-16
Prepare proxy forms and make them available to members on request | At least 14 days prior to AGM | 2024-06-16
Receive nominations for management committee positions to be elected at the AGM | At least 14 days prior to AGM | 2024-06-16
Make a list of all management committee candidates’ names in alphabetical order, with the names of the members who nominated each candidate, open for inspection by members (e.g. noticeboard) | At least 7 days prior to AGM | 2024-06-23
Prepare the official agenda, including only the business that was included on the notice of AGM | At least 7 days prior to AGM | 2024-06-23
Prepare ballot forms for any elections or motions to be determined by secret ballot at the AGM | At least 7 days prior to AGM | 2024-06-23
Circulate a reminder of the date, time and venue for the AGM | At least 7 days prior to AGM | 2024-06-23
Circulate final reminder of the date, time and venue for the AGM | 1 day prior to AGM | 2024-06-29
AGM |  | 2024-06-30
Finalise AGM minutes and circulate | Within 7 days after AGM | 2024-07-07
Submit Annual Return to the Office of Fair Trading | Within 1 month after AGM | 2024-07-30
Formulas:
Date (proposed) = [Date (proposed), row below]-1
Date (proposed) = [Date (proposed), row above]+7