## Introduction
Risk assessment register
Why risk management is essential
Risk management is a vital aspect of organisation operations. It helps organisations identify, assess and manage potential issues before they impact members, assets or an organisation's reputation. Effective risk management promotes a safer environment, financial stability and operational resilience, supporting the organisation's longevity and success. By undertaking regular risk reviews, organisations can proactively address new and emerging risks, maintaining a high standard of safety and preparedness. This process should be revisited periodically, especially following significant events or operational changes. Engaging members, staff and volunteers in the risk management process raises awareness and fosters a culture of accountability and shared responsibility. To ensure transparency, members can share findings and action plans through regular meetings, newsletters or team briefings. This open communication encourages collective problem-solving, ensures everyone understands the organisation’s priorities and promotes a collaborative approach to safeguarding the future.
Risk management steps
The following steps provide a roadmap for undertaking an impactful risk management assessment.
Steps | Action | Description | Instructions | Link
Step 1 | Choose risk categories | Define your risk categories (e.g. equipment, money, facilities, compliance and governance, people) | Edit the categories in the tab '1. Risk categorisation'
Step 2 | Describe the issue/risk | Briefly describe the identified risk or issue. Be clear and concise, detailing what could go wrong within the selected risk area | Add the risks to the tab 'Risk Assessment' and assign the risk category
Step 3 | Assess likelihood | Determine how likely each identified risk is to occur (likelihood) | Review the likelihood rating table on tab '2. Likelihood ratings' for the definitions. Then fill out the likelihood rating for each risk in the 'Risk assessment' tab
Step 4 | Assess consequence | Determine the potential consequences of each identified risk | Review the consequence descriptors on tab '3. Consequences'. Then fill out the consequences for each risk in the 'Risk assessment' tab
Step 5 | Evaluate risk level | Combine the likelihood and consequence ratings to establish an overall risk rating | The risk assessment will autofill the risk rating based on the likelihood and consequence. Refer to tab '4. Risk matrix' for more information
Step 6 | Write actions/mitigation strategies | Identify actions or strategies that will reduce the risk’s likelihood or consequence. These may include things like regular maintenance, updating policies, financial monitoring or additional training | List actions/mitigation strategies in the 'Risk assessment' tab
Step 7 | Specify the timeframe | Indicate the timeframe for completing the mitigation actions. This can be a specific date or a general timeframe (e.g. “Quarterly Review” or “Immediate”) | List timeframes in the 'Risk assessment' tab
Step 8 | Assign a lead role | Identify the role responsible for managing and implementing the actions. This ensures accountability and clarifies who is in charge of risk mitigation efforts | List lead roles in the 'Risk assessment' tab
Step 9 | Monitor and review | Regularly review and update the risk assessment to ensure it reflects current conditions | Once the risk assessment has been approved and at every review after, update the table in tab '5. Approval'
Step 10 | Communicate and engage | Share findings and actions with members, staff and volunteers | Print or export the PDF of the 'Risk assessment' tab to share
1. Risk categorisation
Risk assessment
2. Likelihood ratings
Risk assessment
Risk assessment
Risk assessment
3. Consequences
4. Risk matrix
5. Approval
Risk assessment

## Risk assessment
Risk Assessment
Organisation name: | My Organisation
Step 1 | Step 2 | Step 3 | Step 4 | Step 5 | Step 6 | Step 7 | Step 8
Risk Category | Issue/Risk | Likelihood | Consequence | Risk Rating | Actions/Mitigation Strategies | Timeframe | Lead Role
Compliance and Governance | Uncertainty around emergency management plan and responsibilities | Possible | Moderate | Medium | Conduct annual reviews of emergency plans and provide practical training | Annual review | Safety Officer
Compliance and Governance | Inadequate supervision of children leading to abuse, injury or illness | Possible | Catastrophic | High | Require Working with Children and police checks for all new staff and volunteers working with children, verify referees before hiring and provide training in Safeguarding Children Policy | Before staff and volunteer commencement | Safety Officer
Equipment | Injury to players caused by rusty soccer goals | Rare | Moderate | Low | Replace rusty goals | Prior to start of next season | Equipment Manager
Equipment | Unsafe kitchen appliances causing electrical or burn hazards | Unlikely | Moderate | Medium | Ensure cords are secured, appliances are damage-free, and conduct monthly site safety checks | Monthly | Facilities Manager
Money | Insufficient funds to cover expenses associated with hosting upcoming tournament | Possible | Moderate | Medium | Organise a dedicated fundraising event to raise funds to cover tournament costs | 3 months prior to tournament date | Treasurer
Money | Misuse of organisation funds due to a lack of financial controls | Possible | Major | High | Implement dual sign-off for payments, conduct regular financial audits, enforce a transparent financial reporting system and ensure separation of financial duties | Immediate and ongoing | Treasurer
People | Injury due to incorrect lifting of training equipment or boxes | Possible | Moderate | Medium | Provide training and require two-person lifts for heavy items | Before staff and volunteer commencement | Volunteer Manager
People | Negative, unlawful or unethical behaviour at the venue | Possible | Moderate | Medium | Implement policies, procedures and a Code of Conduct to prevent harassment and uphold the integrity of the sport | Prior to the season start | President
Programs and Events | Sunburn, heatstroke or dehydration affecting players, staff, volunteers or patrons | Likely | Moderate | High | Provide free water access, shade and trained first aid officers. Implement Extreme Heat Policy | Before summer season | Safety Officer
Programs and Events | Unlawful or unwanted photography of individuals | Likely | Moderate | High | Require signed media consent forms before taking and using images | Before event participation | Marketing Coordinator

## 1. Risk categorisation
Risk categorisation
Risk categories are the key support elements of an organisation's operation. As every organisation is different, your organisation may choose to add or remove elements to meet your specific needs. The following table provides some risk examples that fall under each identified category. These can be expanded to meet the unique circumstances of your organisation.
Edit the list below if you would like to adjust your risk categories.
Category | Examples
Equipment | Safety: Regular inspections and maintenance of sports equipment to avoid injuries. Inventory management: Loss or theft of equipment affecting organisation operations. Suitability: Ensuring equipment is appropriate and in good condition for its intended use.
Money | Budgeting: Shortfalls from membership fees affecting organisation viability. Fraud prevention: Misuse of organisation funds due to a lack of financial controls. Financial reporting: Inaccurate records leading to compliance issues with stakeholders or regulators.
Facilities | Maintenance: Unsafe or deteriorating facilities that could lead to injuries. Security: Vandalism or unauthorised access to organisation premises. Accessibility: Facilities not meeting accessibility requirements for all users.
Compliance and Governance | Legal requirements: Failure to comply with regulations (e.g. insurance). Policies and procedures: Outdated or missing policies can create inconsistent practices. Record keeping: Poor documentation can leas to a lack of accountability in decision-making.
People | Training: Lack of safety training for volunteers or staff working with members. Retention: High turnover of volunteers impacting organisation activities. Health and safety: Inadequate procedures for handling injuries or emergencies.
Programs and Events | Event planning: Poor scheduling or organisation causing cancellations or low turnout. Participant safety: Weather events, accidents or negligence resulting in injuries during organisation events or competitions. Regulatory compliance: Failure to obtain necessary permits or adhere to local regulations, leading to fines or event shutdowns.
Other | Edit this category to suit your organisation's needs

## 2. Likelihood ratings
Likelihood ratings
A likelihood rating is a measure used to assess how probable it is that a particular risk will occur. In risk management, this rating helps organisations understand and prioritise risks based on their chances of happening, from highly likely events to rare occurrences. A likelihood rating, such as the one in the following table, is assigned to categorise risk probability.
| Level | Rating
| A | Almost Certain
| B | Likely
| C | Possible
| D | Unlikely
| E | Rare

## 3. Consequences
Consequence descriptors
A consequence rating assesses the potential impact of a risk if it occurs, helping organisations understand the severity of different risks. By rating consequences, organisations can prioritise actions to minimise disruptions, safety hazards or financial strain. Each risk is assigned a consequence level, typically ranging from Insignificant to Catastrophic. Each of these levels is presented below, along with a description of its potential impact across different risk categories.
| Equipment | Money | Facilities | Compliance and Governance | People | Programs and Events
Catastrophic | Major equipment failure causing multiple injuries, significant service interruption, or necessitating total replacement | Financial loss, severely impacting operations or leading to potential insolvency | Facility loss due to severe damage (e.g. fire, flood), making it unusable long-term | Major legal or compliance breach resulting in significant regulatory fines or operational shutdown | Severe incident resulting in fatality or long-term disability | Complete event failure leading to reputational damage or major injury
Major | Recurrent equipment issues leading to member dissatisfaction, minor injuries or costly repairs | Significant financial impact, possibly requiring program cuts or workforce reduction | Major repairs needed due to significant facility issues, impacting organisation activities | Significant policy breach leading to regulatory intervention | Multiple injuries requiring hospitalisation and impacting morale | Significant event disruptions resulting in financial loss and reputational damage
Moderate | Single equipment malfunction causing minor injury or service delay | Unforeseen expenses or funding reductions causing moderate impact | Delayed maintenance causing minor disruptions | Multiple policy violations requiring corrective action | Minor injuries or incidents causing temporary morale issues | Event delays, lower-than-expected attendance or logistical issues causing moderate dissatisfaction
Minor | Slight wear and tear causing temporary disruption with minimal repair costs | Budget impact manageable within existing financial planning | Routine maintenance issues causing negligible disruption | Minor compliance issues resolved internally without external impact | Single minor injury with minimal morale impact | Minor event disruptions causing negligible impact on participant experience
Insignificant | Cosmetic damage with no effect on usability or safety | Minimal financial impact absorbed within the regular budget | Minor wear with no effect on usability or safety | Minor lapse with no significant consequences | No measurable impact on health or morale | No measurable impact on event success

## 4. Risk matrix
Risk matrix
The risk assessment spreadsheet will autofill the risk rating based on the intersection of the likelihood and consequence ratings to reveal the overall risk rating (Low, Medium, High or Extreme), as per the table below.
Consequence
Likelihood | 1: Insignificant | 2: Minor | 3: Moderate | 4: Major | 5: Catastrophic
A: Almost Certain
B: Likely
C: Possible
D: Unlikely
E: Rare
A risk rating is assigned to each risk according to its position on the risk rating matrix. Risks in a green square are lower, risks in a yellow square are medium, risks in an amber square are high and risks in a red square are extreme, as per the following legend:
Low
Medium
High
Extreme

## 5. Approval
Document control
Once the Risk Assessment has been approved by the management committee, and at every review after, enter the date and name of the confirming committee member below.
| Document Approved Date | Confirm by | Summary of change
Issue 1 | Date of approval | Name of committee member responsible
Issue 2