## RISK M'MENT PLAN
RISK MANAGEMENT PLAN <YEAR, EVENT NAME> <Event date>
Risk Assessment compiled by: Name, role
Assumptions: All Stakeholders to review this risk assessment to ascertain their responsibility and ability to implement treatment options. All documents, plans, policies, procedures, staffing levels, training and support referred to and or required to ensure the treatments are effective as intended, will be in place. All persons working to implement the proposed treatments will do so to the best of their ability and as well as can be reasonably expected.
Inclusions: This risk assessment covers the <Event name> delivered by <Organisation name> at the <Venue name> on <Event date>.
Exclusions: This risk assessment does not cover the risks associated with <XXX>
Num | Risk What can go wrong? | Consequences | Responsibility Internal (Inside Organisation) | Responsibility External (Outside of Organisation) | Risk rating (Low, medium, high, extreme) | Mitigation Plan Description What will we do to prevent it? | Risk rating with controls | Action Plan What will we do if it happens?
1 | ADMINISTRATION AND FINANCE
A | E.g. Event team not able to answer enquiries due to lack of knowledge | Incorrect / insufficient information given to public and adverse publicity for Organisers |  |  | Low | Ensure event team has up to date information on Event Overview to respond to enquiries. Ensure reception is briefed immediately of any changes to the program. Reception to forward difficult enquiries to Coordinator if required. | Low | Event team to forward difficult enquiries to Coordinator that they cannot answer.
Low number of nominations received | E.g. Low number of nominations received | Insufficient nominations to judge or inappropriate nominations to award. |  |  | Low | Evaluate previous year's success rate and nomination numbers and develop a targeted marketing database. Monitor nomination numbers in each category during the nominations period. Review communication plan and implement new marketing activities as required. | Low | Extend nomination period and implement new marketing techniques. Encourage nominations through targeted phone calls. Request advice from judging panel on how to contact target markets.
| E.g. Low attendance numbers | Adverse publicity for organisers Disappointment to guests and other stakeholders. |  |  | Low
| E.g. Breach of contract - goods / services | Submitted invoice exceeds approved quotation and contracted amount which may result in budget overspend. Funds need to be sought from another budget Suppliers not paid on time - Supplier will not deliver goods or services, may charge interest. Will not work with Organiser in the future. |  | Supplier/s | Low
3 | PROGRAMMING AND PRODUCTION
N | E.g. Guests without tickets try to attend event | Potential disgruntled guest. |  |  | Low
Y | E.g. Key stakeholder withdraws from event | Event program changes significantly. |  | Stakeholder/s | Medium
5 | PUBLIC RELATIONS, MARKETING AND COMMUNICATION
| E.g. Misinformation published / distributed to attendees | Potential attendees communicated incorrect information. |  | Media | Low
| E.g. Media not able to access event site | No media stories / footage from event. |  | Media | Low
| E.g. Comments from the general public on social media inappropriate or offensive. | Distract attention from event. Negative publicity for Queensland Government. |  |  | Low
| E.g. Questions from the general public on social media not answered. | Potential for Queensland Government to receive negative publicity about ignoring public comments. |  |  | Low
| E.g. Photo published without consent | Possible legal action from guest / performer if photo is published from events without consent. |  |  | Low
C | E.g. Mobile phone tower network access is slowed due to crowd size concentration and location. | Staff, suppliers and QPS unable to communicate via mobile phone. Disgruntled guests. |  | Network Provider
D | Two way radios - handset and accessories fail. | Staff and suppliers unable to communicate via radio on site. |  | Supplier
E | Two way radios - use of open microphones results in member of the public overhearing sensitive or inappropriate information. | Adverse publicity or complaints against the Queensland Government. Confidential information is made public. |  | Supplier
F | E.g. Project Coordinator or Event Manager's mobile phone breaks, is lost or battery runs flat. | Staff and suppliers unable to communicate directly with the PC via mobile phone on site or in the lead up to the event. |  |  | Low
H | E.g. Computer access is restricted or Wi-Fi not available in week prior to or on day of event. | Inability to access key documents and databases. |  | IT Services | Low
6 | HUMAN RESOURCES
A | E.g. Key staff sick or has to take unplanned leave in lead up to project or on event date | Delays in progress and event planning momentum. Key information and rapport with key stakeholders lost. Delay whilst new PC is allocated to project. Key information is lost. Key staff roles are vacant, other staff need to step into a new role without proper briefing. |  |  | Low
D | E.g. Staff resources insufficient for size of project or available staff inexperienced and project delivery is compromised. | Timelines are not met and key event tasks not completed or not completed correctly. Overspend on budget with staff on overtime. Staff carry out work incorrectly, or incorrect information is given to guests. Possible adverse publicity for Queensland Government. |  |  | Low
H | E.g. Suppliers do not show or are late | Key elements of event are inoperable or not set up. |  | Venue, Supplier/s | Medium
9 | HEALTH AND SAFETY
B | E.g. Management or staff member injured or sick during the bump in or bump out phase or during event. | Interruption to the event's bump-in process. Lost Time Injury (LTI) or possible Workers Compensation claim. Possible delays in removing infrastructure from venue. Adverse publicity for Queensland Government. |  | Venue, Supplier/s | Low
D | E.g. Supplier injured during the bump in or bump out phase or during event. (Workplace injury or illness, absenteeism) | Supplier management or worker becomes sick, unable to work or records a Lost Time Injury (LTI). Possible partial / total loss of certain services during bump in / out phase. |  | Venue, Supplier | Low
J | E.g. Injury during pre or post event production bump in or out process. | Injury claim against Queensland Government. Negative publicity against the DPC. |  | Venue, Supplier/s | Low
N | E.g. inadequate accessibility to event for people with disabilities, sight impairment, hearing impairment. | Adverse publicity for Queensland Government. Complaint made by event attendee. Event attendees have a negative experience. |  |  | Low
S | E.g. Electrical Tagging & Testing of leads and distribution boards. Use of cable trays to house electrical leads in a safe and measured manner. | Electricity fails due to faulty cord. Fire occurs because of faulty cord. |  | Venue, Supplier/s | Low
| E.g. Hygiene standards, food service and dietary requirements not adhered to | Illness to guests or staff. Adverse media for Queensland Government. Poor reflection of DPC and event. |  | Venue, Supplier/s | Low
11 | SECURITY
C | E.g. Bomb threat called in to venue | Patrons evacuated from event site. |  | Venue, QPS | High
E | E.g. Patrons do not adhere to evacuation. | Patrons in danger of relevant threat. |  | Venue, QPS | Low
I | E.g. Impromptu events, protests, rally etc | Adverse publicity for Queensland Government. Possible injury to attendee. Possible disruption to the event. Affects the experience of the event attendees. |  | Venue, QPS | Medium
| E.g. Audio sound levels | Breach of Environmental Protection Act regulations. Attendees may suffer discomfort or temporary hearing damage due to excessive sound levels. Neighbours disgruntled. |  | Technical Production Supplier | Medium
| E.g. Guest has medical emergency. | Medical emergency occurs at event. |  | Venue, First Aid, QAS | Medium
| E.g. Equipment falls or becomes loose. | Staff, guest or performer injured. |  | Event Suppliers | Medium
| E.g. Staff/guests/ suppliers suffer from exhaustion. | Staff, guests, suppliers becomes sick, unable to attend event |  | Event Suppliers | Medium
| E.g. Staff member injured lifting heavy items. | Staff member unable to work, workers compensation claim. |  | Event Suppliers | Medium
TRAFFIC AND TRANSPORT
| E.g. Pedestrian access restricted. | Pedestrians unable to move freely around event site due to over crowding or closed access. |  | Venue | Medium
| E.g. VIP unable to access site | Lack of transport |  | Venue | Medium
|  | Arrives late |  | DPC | Medium
| E.g. Emergency vehicle requires access to the site, however entry point is blocked. | Emergency entry points/exits not accessible in emergency. |  | Venue | Medium

## Risk Analysis
Risk Analysis and Assessment
Once risks are identified, they are evaluated on a 2 dimensional matrix using a qualitative rating of the impact of the risk and likelihood of the risk occurring.
When risks have been identified, they are analysed by combining the impact and likelihood to produce an overall level of risk.
This form of evaluation provides a good graphical representation of how serious the risk is or where it lies within a group of risks.
The risk analysis provides information critical to determining what risks need to be treated and what risks are accepted.
The following matrices have been utilised for the assessment and evaluation process.
Level of Risk
Impact
Likelihood | Insignificant 1 | Minor 2 | Moderate 3 | Major 4 | Catastrophic 5
1 (rare) | Low | Low | Medium | High | High
2 (unlikely) | Low | Low | Medium | High | Extreme
3 (moderate) | Low | Medium | High | Extreme | Extreme
4 (likely) | Medium | High | High | Extreme | Extreme
5 (almost certain) | Medium | High | Extreme | Extreme | Extreme
Risks identified as extreme, and in some cases high, should be addressed immediately and a risk action plan completed. All risks should be assessed in terms of their priority and those with the highest priority should be addressed first, followed by lower priority risks.

## Sheet1 (hidden)
B | Great Australian Bites Friday 24th January, 2014 from 5:00 to 21:30 hours. | Injury claim against Queensland Government. Negative publicity against the DPC. | EC | SBP | 3 | 3 | Medium | Administrative | Multicultural ticketed event for a nominated number of patrons (500) with Security provided for safety and security. BBQ cooking demonstrations in a relaxed dining experience. Strict adherence to RSA principles reducing the likelihood of Alcohol Fuelled Violence. | Multicultural ticketed event for a nominated number of patrons (500) with Security provided for safety and security. BBQ cooking demonstrations in a relaxed dining experience. Strict adherence to RSA principles reducing the likelihood of Alcohol Fuelled Violence. | 2 | 2 | Low | Defer to ABP Security protocols in relation to any incident or emergency at this location. | PC, EM | ü | ü | ü
C | Australia Day Festival at Southbank Sunday 26th from 10:00 to 19:30 hours. | Injury claim against Queensland Government. Negative publicity against the DPC. | EC | SBP | 3 | 3 | Medium | Administrative | Events Coordination, Department of Premier and Cabinet will partner with venues to provide a program of free entertainment including: - live music - art installations - creative shows and activities | Events Coordination, Department of Premier and Cabinet will partner with venues to provide a program of free entertainment including: - live music - art installations - creative shows and activities | 2 | 2 | Low | Defer to the SBP Security protocols in conjunction with the QPS contingent onsite. | PC, EM | ü | ü | ü
D | Flag Raising Ceremony Sunday 26th from 11:15 to 12:15 hours | Security Teams facilitating the Queensland Government personnel. Negative publicity against the DPC. | EC | ADF, QPS & SBP | 5 | 4 | High | Administrative & Engineering | Traditional flag raising ceremony - QPS to secure location and provide security with ABP staff. The ADF, Governor General, QLD Premier and other VIP's in attendance. | Traditional flag raising ceremony - QPS to secure location and provide security with ABP staff. The ADF, Governor General, QLD Premier and other VIP's in attendance. | 3 | 4 | High | Defer to SBP security protocols. QPS Security details to respond and take Forward Command of any credible threat against the event or a protected person. | PC, EM, DEC |  |  | ü
E | 21 Gun Salute Sunday 26th from 12:00 noon to 12:15 hours. | Injury claim against Queensland Government. Negative publicity against the DPC. | EC | ADF | 5 | 4 | High | Administrative & Engineering | Exclusion zones to be erected around gun firing area at Southbank. Only ADF personnel to operate within the exclusion zone. QWPS to maintain an exclusion zone on the Brisbane River. The EM, QPS and ADF to assemble together and maintain two way radio contact at all times to respond to any breaches of the zone or until the salute has been completed.. | Exclusion zones to be erected around gun firing area at Southbank. Only ADF personnel to operate within the exclusion zone. QWPS to maintain an exclusion zone on the Brisbane River. The EM, QPS and ADF to assemble together and maintain two way radio contact at all times to respond to any breaches of the zone or until the salute has been completed.. | 3 | 3 | Medium | In the case of a misfire, EC to follow instructions of ADF and EC. EC to liaise with traffic control management and maintain the exclusion zone. If suppliers / vendors cannot produce MSDS, the hazardous material to be removed from site. If injury occurs from a hazardous material, follow instructions listed on the MSDS. | PC, EM, DEC |  |  | ü
H | RAAF flypast featuring a FA18 hornet over the South Bank site. 12:00 noon sharp. | Injury from falling object. Noise complaints from unsuspecting persons. Injury claim against ADF and / or Queensland Govt. | EC | RAAF | 2 | 5 | Medium |  | The ADF will manage this process and lead any response to an incident in conjunction with SBP and QPS, | The ADF will manage this process and lead any response to an incident in conjunction with SBP and QPS, | 2 | 2 | Low | Public Address system updating patrons and the public of impending arrival of a jet over head. The ADF handing out ear plugs in the Cultural Forecourt area prior to the fly past. | PC, EM |  |  | ü
A | Adverse publicity for Queensland Government and financial loss to the department. | Promotional and financial liability to the state. | EC | SBP, Suppliers, QPS, ADF | 3 | 4 | Extreme | Administrative | GENERAL/PUBLIC - Follow processes during planning and onsite. - Volunteers required to sign a 'conditions of participation in event' form approved by CALS. - The Australia Day Festival is an all ages, alcohol free event is included on all pre-event signage and promotion. This is also included on all key Festival signage (tri-sigs) installed for the event day. | GENERAL - Ensure all processes are followed in the planning and delivery of event, and any issues are documented for debrief and post event review. All participating volunteers required to sign a 'conditions of participation in event' form approved by CALS. The Australia Day Festival is an all ages, alcohol free event' is included on all pre-event signage. This is also included on all key Festival signage (tri-sigs) installed for the event day. | 3 | 2 | Medium | Collect all details of the complaint and ensure the complaint is dealt with, followed up and a response is issued, if required. Record information in event report for post event review. | EM, DEC, MM | ü | ü | ü
[5 empty] | 3 | 4 | Extreme | Administrative | FLAG RAISING - A Deed of Indemnity is signed amongst the Commonwealth, State and the SBP to cover liability issues surrounding the gun salute and ceremony elements. | FLAG RAISING - A Deed of Indemnity is signed amongst the Commonwealth, State and the SBP to cover liability issues surrounding the gun salute and ceremony elements. | 3 | 2 | Medium | DPC to complete | DPC to complete |  |  | ü
[5 empty] | 3 | 4 | Extreme | Administrative | FESTIVAL Public Liability Insurance required and certificates of currency requested from entertainers and workshops. - SBP to provide online induction for EC staff. - SBP to ensure suppliers review and agree to Work Place Health and Safety manual before working on site. | FESTIVAL Public Liability Insurance required and certificates of currency requested from entertainers and workshops. - SBP to provide online induction for EC staff. - SBP to ensure suppliers review and agree to Work Place Health and Safety manual before working on site. | 3 | 1 | Medium | Refer any valid complaint to the appropriate department for further action. | EM, DEC | ü | ü
| Great Australian Bites | Friday 24 January 1700 hours to 2100 hours
1 x Stage
2 x dressing rooms ( 2 Pagodas)
Bar Marquee ( 39 m x 6 m )
VIP Bar
2 x small Bars
Food Stalls x 6 ( 3x3 structures )
MMM Activation
2 x 6 m x 3 m Portable Toilet Suites
1 Video Screen
Sirromet Tasting Activations
1 ATM
Food Demonstration Area
| Australia Day Festival | Sunday 26 January 2014 10:00 hours to 19:30 hours
Main Stage - Southbank Forecourt
Conservatorium Stage
Forest Green Stage
Courier mail Piazza - Area
Stage - Southbank Forecourt
VIP Marquee
VIP reception (Pagoda)
| Australia Day Flag Raising Ceremony | Sunday 26 January 2014 11:15 hours to 12:15 hours
Dias - Lectern, Flagpole, ADF band
VIP Marquee & seated area
VIP reception (Pagoda)
Guns for a 21 Gun Salute (ADF)
Temporary Fencing
Banana Bat Installation